## PMO Dashboard
ASSISTANT PMO — PROJECT CONTROL DASHBOARD
Purpose | Single source of truth for project status, risks, issues, actions, changes, cost and schedule. |  |  | Weekly Executive Summary
Update cadence | Daily: actions/issues ¦ Weekly: project status ¦ Monthly: management review |  |  | Overall status | Green / Yellow / Red
|  |  |  | Top achievement | What was completed this week
KPI | Value | KPI | Value | Top risk | What may affect delivery
Active Projects |  | Red Projects |  | Top issue | Current blocker requiring action
Yellow Projects |  | Open Risks |  | Decision required | Management decision needed
Open Issues |  | Overdue Actions |  | Next milestone | Date + milestone
Status Legend
Green
Yellow
Red

## Project Register
PROJECT REGISTER
Project ID | Project Name | Sponsor | Project Manager | Department | Start Date | Target End Date | Status | RAG | % Complete | Budget | Actual Cost | Next Milestone | Notes
PRJ-001 | ERP Implementation | CEO | Project Manager | IT | 2026-10-01 | 2026-12-30 | Active | Green | 35% | 500000 | 160000 | UAT | Sample row — replace with your project
PRJ-002 | Network Upgrade | Operations Director | IT Lead | IT | 2026-10-05 | 2026-11-20 | Active | Yellow | 30% | 180000 | 95000 | Switch installation | Vendor delivery risk

## Project Charter
PROJECT CHARTER TEMPLATE
Project Name
Project Sponsor
Project Manager
Business Owner
Problem / Opportunity
Business Objective
Expected Benefits
High-Level Scope
Out of Scope
Key Deliverables
Target Start
Target End
Budget
Key Milestones
Major Risks
Key Stakeholders
Approval / Go-No-Go

## WBS & Schedule
WBS + GANTT / SCHEDULE TRACKER
WBS ID | Task / Deliverable | Owner | Dependency | Start | Finish | Duration (days) | % Complete | Status | Baseline Finish | Variance (days) | Milestone? | Notes
1.0 | Project Initiation | PM |  | 2026-10-01 | 2026-10-03 | 3 | 100% | Complete | 2026-10-03 |  | Yes
2.0 | Requirements | Business Analyst | 1.0 | 2026-10-04 | 2026-10-10 | 7 | 80% | In Progress | 2026-10-10 |  | Yes
3.0 | Development | Development Team | 2.0 | 2026-10-11 | 2026-11-05 | 26 | 35% | In Progress | 2026-11-05 |  | No
4.0 | Testing / UAT | QA + Users | 3.0 | 2026-11-06 | 2026-11-20 | 15 | 0% | Not Started | 2026-11-20 |  | Yes

## RAID Log
RAID LOG — RISKS, ASSUMPTIONS, ISSUES, DEPENDENCIES
ID | Type | Description | Impact | Probability | Severity | Owner | Response / Action | Due Date | Status | Escalation? | Date Raised | Resolution / Outcome | Notes
R-001 | Risk | Vendor delivery delay | High | High | High | Procurement | Confirm delivery and prepare alternative supplier | 2026-10-12 | Open | Yes | 2026-10-08
I-001 | Issue | UAT environment not ready | High | High | High | IT Lead | Complete server configuration | 2026-10-11 | Open | Yes | 2026-10-08
A-001 | Assumption | Users available for UAT | Medium | Medium | Medium | Business Owner | Confirm user availability | 2026-10-15 | Open | No | 2026-10-08
D-001 | Dependency | Payment gateway approval | High | Medium | High | Finance | Follow up with provider | 2026-10-18 | Open | Yes | 2026-10-08

## RACI Matrix
RACI MATRIX
Activity / Deliverable | Sponsor | PM | Business Owner | IT/Technical | Finance | Procurement | QA | Users | Notes
Project Charter | A | R | C | C | I | I | I | I
Requirements | I | A | R | C | C | I | C | C
Development | I | A | C | R | I | I | C | I
UAT | I | A | R | C | I | I | R | R
Go-Live Approval | A | R | C | C | C | I | C | C
R = Responsible ¦ A = Accountable ¦ C = Consulted ¦ I = Informed

## Action Tracker
ACTION / DECISION TRACKER
Action ID | Project | Action / Decision | Owner | Priority | Date Opened | Due Date | Completed Date | Status | Days Late | Escalation? | Notes
ACT-001 | ERP Implementation | Confirm UAT users | Business Owner | High | 2026-10-08 | 2026-10-10 |  | Open |  | Yes
ACT-002 | Network Upgrade | Confirm switch delivery | Procurement | High | 2026-10-08 | 2026-10-12 |  | Open |  | Yes
Formulas:
Days Late = IF(AND([Status]<>"Closed",[Due Date]<TODAY()),TODAY()-[Due Date],0)

## Change Log
CHANGE REQUEST / CHANGE CONTROL
CR ID | Project | Requested By | Date | Change Description | Reason | Scope Impact | Schedule Impact | Cost Impact | Risk Impact | Approval | Implementation Status | Notes
CR-001 | ERP Implementation | Business Owner | 2026-10-08 | Add payroll report | New reporting requirement | Medium | 3 days | 25000 | Medium | Pending | Not Started
Rule: No material scope/schedule/cost change should be implemented without impact assessment and approval.

## Cost Tracker
COST / BUDGET TRACKER
Project | Cost Category | Budget | Committed | Actual | Forecast at Completion | Variance vs Budget | Owner | Status | Notes
ERP Implementation | Software | 200000 | 180000 | 150000 | 180000 |  | Finance | Green
ERP Implementation | Hardware | 300000 | 250000 | 10000 | 270000 |  | IT | Green
Network Upgrade | Equipment | 150000 | 140000 | 95000 | 160000 |  | IT | Yellow

## Weekly Status Report
WEEKLY PROJECT STATUS REPORT
Reporting Week
Project
Project Manager
Overall RAG
Progress This Week
Completed
Next Week
Key Milestone
Schedule Status
Cost Status
Scope Status
Quality Status
Top Risks
Top Issues
Decisions Required
Support Required
Executive Summary

## Meeting Minutes
MEETING MINUTES + ACTIONS
Meeting Date | Meeting Type | Project | Chair | Attendees | Agenda | Decision / Discussion | Action / Owner | Due Date

## Stakeholder Register
STAKEHOLDER REGISTER + COMMUNICATION PLAN
Stakeholder | Role | Department | Influence | Interest | Information Needed | Frequency | Channel | Owner | Engagement Strategy
CEO | Sponsor | Executive | High | High | Executive status, risks, decisions | Weekly | Email/Meeting | PMO | Manage closely
Business Owner | Owner | Business | High | High | Scope, progress, UAT, issues | Weekly | Meeting/Teams | PMO | Manage closely
Technical Lead | Delivery | IT | Medium | High | Tasks, blockers, technical risks | Daily/Weekly | Teams/Meeting | PMO | Keep engaged

## Quality Checklist
QUALITY / DELIVERABLE ACCEPTANCE CHECKLIST
Project | Deliverable | Quality Check | Owner | Planned Date | Actual Date | Result | Evidence / Link | Notes
ERP Implementation | Requirements | Business requirements approved | Business Owner | 2026-10-10 |  | Pending
ERP Implementation | UAT | Critical test cases passed | QA | 2026-11-20 |  | Pending
ERP Implementation | Go-Live | Backup and rollback tested | IT | 2026-12-20 |  | Pending

## Procurement Tracker
PROCUREMENT TRACKER
Req ID | Project | Item / Service | Requester | Supplier | Quotation | PO No. | Budget | Quoted Cost | Order Date | Expected Delivery | Status
PR-001 | ERP Implementation | Application Server | IT | Vendor A | Received | PO-001 | 250000 | 245000 | 2026-10-08 | 2026-10-20 | Ordered
PR-002 | Network Upgrade | Managed Switches | IT | Vendor B | Pending |  | 150000 | 0 |  | 2026-10-18 | Quotation

## Lessons Learned
LESSONS LEARNED / CONTINUOUS IMPROVEMENT
Project | Date | Area | What Happened | Impact | Lesson | Action for Future Projects

## PMO Daily Weekly SOP
ASSISTANT PMO DAILY / WEEKLY OPERATING SYSTEM
Frequency | Activity | What Good Looks Like
Daily | Check dashboard | Review red/yellow projects and upcoming deadlines.
Daily | Update actions | Chase owners for overdue or due-soon actions.
Daily | Capture decisions | Record decisions, owners and due dates from meetings.
Daily | Escalate blockers | Escalate issues when owner cannot resolve within agreed time.
Monday | Project review | Review all project schedules, milestones and dependencies.
Tuesday | Risk & issue review | Review RAID log and mitigation actions.
Wednesday | Stakeholder follow-up | Confirm progress with project managers / owners.
Thursday | Report preparation | Prepare weekly status and executive summary.
Friday | PMO reporting | Publish status, update dashboard and archive evidence.
Monthly | Management review | Review portfolio performance, budget, risks and trends.

## 30-60-90 Day Plan
ASSISTANT PMO — 30 / 60 / 90 DAY PLAN
Period | Focus | Actions | Deliverables | Success Measure | Notes
Days 1–30 | Learn + Stabilize | Understand portfolio; meet PMs; map reporting; create project register; learn tools and approval workflows | Master dashboard, RAID, action tracker, meeting minutes | 100% active projects registered; weekly reporting running
Days 31–60 | Control + Improve | Standardize status reports; introduce RACI/WBS; improve risk and change control; automate follow-ups | PMO templates + consistent reporting cadence | Fewer overdue actions; risks visible before becoming issues
Days 61–90 | Optimize + Lead | Portfolio trends; KPI reporting; lessons learned; process improvement; support management decisions | Executive dashboard + PMO improvement plan | Management receives reliable, decision-ready information

## START HERE
START HERE — ASSISTANT PMO QUICK GUIDE
Step | Tool | What to Do
1 | Open Project Register | Enter every active project. Do not manage projects that are invisible.
2 | Create/update WBS & Schedule | Track tasks, dependencies, milestones, baseline and variance.
3 | Maintain RAID Log | Every significant risk/issue/assumption/dependency gets an owner and due date.
4 | Maintain Action Tracker | Every action has one owner and one due date.
5 | Use Change Log | Record requested changes and complete impact assessment before approval.
6 | Update Cost Tracker | Compare budget, committed, actual and forecast.
7 | Run weekly status | Summarize progress, RAG, risks, issues, decisions and next milestones.
8 | Use Meeting Minutes | Record decisions and actions immediately.
9 | Escalate professionally | State problem → impact → action → owner → decision required.
10 | Close properly | Get sign-off, archive documents and capture lessons learned.